## Schedule
MTC GENERAL CONTRACTOR — CONSTRUCTION SCHEDULE · AVIANCA
Confidential document
CLIENT | Avianca |  | CONTACT | Nancy Calderón
LOCATION | Suites 203, 204, 205, 209, 210 & 211 |  | ESTIMATED START | Aug 3, 2026
ESTIMATED DURATION | ≈ 6 weeks |  | OVERALL PROGRESS | 0%
Commercial terms: Work will commence upon receipt of the 50% advance payment. · Dumpster locations for demolition debris will be coordinated with Avianca.
Phase |  | Suite | Activity | Period | Status
01 | Demolition & new walls — Pending · 0% |  |  | Aug 10 – 15, 2026
|  | 209 | Provide, install & modify (3) new accordion doors in the security area | Aug 10 – 15, 2026 | —
|  | 209 | Remove walls from Security GM & Supervisor office (back of the room) | Aug 10 – 15, 2026 | —
|  | 209 | Provide new wall (10 LF) for security closet, customized to fit approx. 75" tall | Aug 10 – 15, 2026 | —
|  | 211 | Interior partition demolition | Aug 10 – 15, 2026 | —
|  | 211 | Install new wall, 8 LF (to match existing wall level, not from F.F. to RCP) | Aug 10 – 15, 2026 | —
|  | 211 | Patch and paint (Print Room & Supervisor office) | Aug 10 – 15, 2026 | —
02 | Security door — Suite 204 — Pending · 0% |  |  | Aug 17 – 22, 2026
|  | 204 | Install a lockable door in the security area | Aug 17 – 22, 2026 | —
|  | 204 | Repair walls and paint | Aug 17 – 22, 2026 | —
03 | Security rooms build-out — Pending · 0% |  |  | Aug 24 – 29, 2026
|  | 209 | Patch and paint walls (color provided by Avianca) | Aug 24 – 29, 2026 | —
|  | 209 | Coordinate with Avianca dumpster locations for demo debris | Aug 24 – 29, 2026 | —
|  | 203 | Frame new opening for new door | Aug 24 – 29, 2026 | —
|  | 203 | Frame new wall, 6 LF (to match top level of existing wall) | Aug 24 – 29, 2026 | —
|  | 203 | Provide and install (1) customized folding door for storage | Aug 24 – 29, 2026 | —
|  | 203 | Data drop install (1) | Aug 24 – 29, 2026 | —
|  | 203 | Power drop (1) | Aug 24 – 29, 2026 | —
|  | 203 | Relocate (1) light switch next to new door | Aug 24 – 29, 2026 | —
|  | 203 | Provide and install (1) 2'×2' light (match existing) | Aug 24 – 29, 2026 | —
|  | 205 | Secure & install (3) new 2'×2' lights | Aug 24 – 29, 2026 | —
|  | 205 | Provide one CCTV drop (1) | Aug 24 – 29, 2026 | —
|  | 205 | Provide one data drop (1) | Aug 24 – 29, 2026 | —
|  | 205 | Provide & install new interior door & frame, 36", between rooms | Aug 24 – 29, 2026 | —
|  | 205 | Patch and paint walls | Aug 24 – 29, 2026 | —
|  | 205 | Coordinate with Avianca dumpster locations for demo debris | Aug 24 – 29, 2026 | —
04 | Flooring & electrical — Suite 210 — Pending · 0% |  |  | Aug 31 – Sep 5, 2026
|  | 210 | Replace door (door provided by Avianca) | Aug 31 – Sep 5, 2026 | —
|  | 210 | Remove flooring, approx. 630 SQFT in 2 layers — laminate & carpet (desk office area and small kitchen) | Aug 31 – Sep 5, 2026 | —
|  | 210 | Patch and paint walls | Aug 31 – Sep 5, 2026 | —
|  | 210 | General painting of Office 210 | Aug 31 – Sep 5, 2026 | —
|  | 210 | Furnish & install new laminate flooring & 5-1/4" base — approx. 630 SQFT & 150 LF of base | Aug 31 – Sep 5, 2026 | —
|  | 210 | Relocate electrical outlets if necessary — outlets for refrigerator, microwave, coffee maker & toaster | Aug 31 – Sep 5, 2026 | —
|  | 210 | Supply and installation of electrical wiring from the office to the electrical room | Aug 31 – Sep 5, 2026 | —
|  | 210 | Supply and installation of (4) new circuit breakers to support additional voltage load | Aug 31 – Sep 5, 2026 | —
|  | 210 | (8) electrical outlets (power points) | Aug 31 – Sep 5, 2026 | —
|  | 210 | (8) data points (low-voltage / data outlets) | Aug 31 – Sep 5, 2026 | —
|  | 210 | Coordinate with Avianca dumpster locations for demo debris | Aug 31 – Sep 5, 2026 | —
05 | Custom door & final paint — Pending · 0% |  |  | Sep 7 – 12, 2026
|  | 211 | New custom door (height aligned with top of wall) | Sep 7 – 12, 2026 | —
|  | 211 | General painting of new walls | Sep 7 – 12, 2026 | —
|  | 211 | Coordinate with Avianca for dumpster locations for demo debris | Sep 7 – 12, 2026 | —
Confidential document. For the exclusive use of Avianca and MTC General Contractor. · Generated: July 29, 2026